## Analysis_Summary
Construction Project Controls Analytics — Analyze Phase
Portfolio-level cost, schedule, change, RFI, and contingency analysis based on synthetic construction project-control data. Findings describe associations within this dataset and must not be presented as construction-industry benchmarks or causal proof.
Projects |  |  | Portfolio BAC |  |  | Forecast EAC |  |  | Forecast Overrun
75 |  |  | 5831436600 |  |  | 6586989965.6969 |  |  | 12.96%
Weighted CPI |  |  | Weighted SPI |  |  | Average Delay |  |  | Contingency Used
0.88417 |  |  | 0.98717 |  |  | 33.68 |  |  | 66.23%
Health Status | Projects
Red | 50
Yellow | 13
Green | 12
Project Type | Projects | Forecast Overrun % | Average Delay Days | [8 empty] | Project Type | Forecast Overrun %
Mixed-Use | 11 | 16.34% | 46.8182 | [8 empty] | Mixed-Use | 16.34%
Residential | 14 | 13.96% | 35 | [8 empty] | Residential | 13.96%
Industrial | 9 | 13.91% | 25.5556 | [8 empty] | Industrial | 13.91%
Commercial | 13 | 12.23% | 30.6923 | [8 empty] | Commercial | 12.23%
Institutional | 18 | 11.27% | 44.9444 | [8 empty] | Institutional | 11.27%
Heavy Civil & Infrastructure | 10 | 9.407% | 8.3 | [8 empty] | Heavy Civil & Infrastructure | 9.407%
Key Analytical Findings
1 | Portfolio cost efficiency | Weighted CPI is 0.884; aggregate EAC is $6.59B, 13.0% above the $5.83B BAC.
2 | Schedule exposure | 50 projects are Red under the approved thresholds, and the average forecast delay is 33.7 days.
3 | Project-type pattern | Mixed-Use has the highest portfolio-weighted forecast overrun at 16.3%; Heavy Civil & Infrastructure is lowest at 9.4%.
4 | RFI response relationship | Average RFI response time has a moderate positive association with schedule delay (Pearson r = 0.517).
5 | Contingency warning signal | Contingency burn ratio has a strong positive association with forecast overrun (Pearson r = 0.901).
6 | Change-order interpretation | Approved change value has a moderate association with forecast overrun (r = 0.400). Cost Growth % is not an independent test because Current Budget is defined as Original Budget plus approved changes.
Top 10 Projects Requiring Management Attention
Rank | Project ID | Project Name | Type | Status | CPI | SPI | Forecast Overrun | Delay Days | Contingency Used | Primary Driver | Risk Triggers
1 | PRJ-075 | Canyon Ridge Transit-Oriented Development | Mixed-Use | Red | 0.75261 | 0.99717 | 32.87% | 73 | 107.1% | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 90%
2 | PRJ-009 | Northstar Housing | Residential | Red | 0.75479 | 1 | 32.49% | 63 | 105.6% | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 90%
3 | PRJ-046 | Red Rock Residences | Residential | Red | 0.77901 | 1 | 28.37% | 84 | 107.1% | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 90%
4 | PRJ-068 | Canyon Ridge Bridge Rehabilitation | Heavy Civil & Infrastructure | Red | 0.79426 | 1 | 25.9% | 55 | 95.45% | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 90%
5 | PRJ-034 | Mountain Gate Community College | Institutional | Red | 0.80532 | 1 | 24.17% | 38 | 91.35% | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 90%
6 | PRJ-017 | Westfield Retail Center | Commercial | Red | 0.8136 | 0.98793 | 22.91% | 48 | 91.57% | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 90%
7 | PRJ-064 | Evergreen Townhomes | Residential | Red | 0.81579 | 1 | 22.58% | 34 | 92.45% | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 90%
8 | PRJ-013 | Sunrise Housing | Residential | Red | 0.81926 | 1 | 22.06% | 61 | 91.72% | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 90%
9 | PRJ-069 | Cedar Valley Town Center | Mixed-Use | Red | 0.84916 | 0.84762 | 17.76% | 104 | 61.12% | CPI < 0.90 | CPI < 0.90; SPI < 0.90; Forecast overrun > 10%; Delay > 30 days
10 | PRJ-025 | Blue Mesa Public Safety Center | Institutional | Red | 0.89271 | 0.86887 | 12.02% | 87 | 33.05% | CPI < 0.90 | CPI < 0.90; SPI < 0.90; Forecast overrun > 10%; Delay > 30 days

## Project_Analysis
Project-Level Cost, Schedule, Change, RFI, and Contingency Analysis
Formula-driven metrics use the latest monthly performance record for each project. Health thresholds match the approved ASK-phase classification rules.
Priority Rank | Project ID | Project Name | Project Type | Delivery Method | Contract Type | Project Status | Current Phase | Original Budget | Current Budget | Planned Value | Earned Value | Actual Cost | Percent Complete | Planned End | Forecast End | Original Contingency | Contingency Used | Approved CO Value | Pending CO Value | RFI Count | Avg RFI Response Days | Late RFI Count | CPI | SPI | Cost Variance | Schedule Variance | EAC | ETC | VAC | Forecast Overrun % | Cost Growth % | Schedule Delay Days | Approved CO % | Pending CO % | Contingency Utilization % | Contingency Burn Ratio | Late RFI Rate | Health Status | Primary Risk Driver | All Risk Triggers
1 | PRJ-075 | Canyon Ridge Transit-Oriented Development | Mixed-Use | Design-Bid-Build | Unknown | Active | Closeout | 104919600 | 108457000 | 104919600 | 104623200 | 139014400 | 99.7 | 2025-11-12 | 2026-01-24 | 6894200 | 7382000 | 3537400 | 856600 | 29 | 15.5862 | 20 | 0.75261 | 0.99717 | -34391200 | -296400 | 139408231.083 | 393831.083 | -34488631.083 | 32.87% | 3.372% | 73 | 3.372% | 0.8164% | 107.1% | 1.074 | 68.97% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 90%
2 | PRJ-009 | Northstar Housing | Residential | Design-Build | Guaranteed Maximum Price | Complete | Closeout | 34594800 | 35471700 | 34594800 | 34594800 | 45833700 | 100 | 2023-04-12 | 2023-06-14 | 2739400 | 2892700 | 876900 | 363700 | 28 | 18.75 | 23 | 0.75479 | 1 | -11238900 | 0 | 45833700 | 0 | -11238900 | 32.49% | 2.535% | 63 | 2.535% | 1.051% | 105.6% | 1.056 | 82.14% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 90%
3 | PRJ-046 | Red Rock Residences | Residential | Design-Build | Lump Sum | Complete | Closeout | 64273500 | 66560500 | 64273500 | 64273500 | 82506800 | 100 | 2023-05-20 | 2023-08-12 | 5073200 | 5433100 | 2287000 | 48500 | 20 | 15.95 | 16 | 0.77901 | 1 | -18233300 | 0 | 82506800 | 0 | -18233300 | 28.37% | 3.558% | 84 | 3.558% | 0.07546% | 107.1% | 1.0709 | 80% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 90%
4 | PRJ-068 | Canyon Ridge Bridge Rehabilitation | Heavy Civil & Infrastructure | Design-Bid-Build | Unit Price | Complete | Closeout | 54366700 | 56660800 | 54366700 | 54366700 | 68449800 | 100 | 2024-08-04 | 2024-09-28 | 2718500 | 2594800 | 2164000 | 478500 | 31 | 17.0968 | 26 | 0.79426 | 1 | -14083100 | 0 | 68449800 | 0 | -14083100 | 25.9% | 4.22% | 55 | 3.98% | 0.8801% | 95.45% | 0.9545 | 83.87% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 90%
5 | PRJ-034 | Mountain Gate Community College | Institutional | CMAR | Unit Price | Complete | Closeout | 59981900 | 62406100 | 59981900 | 59981900 | 74482300 | 100 | 2024-06-09 | 2024-07-17 | 4517500 | 4126800 | 2424200 | 388000 | 25 | 15.44 | 21 | 0.80532 | 1 | -14500400 | 0 | 74482300 | 0 | -14500400 | 24.17% | 4.042% | 38 | 4.042% | 0.6469% | 91.35% | 0.91351 | 84% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 90%
6 | PRJ-017 | Westfield Retail Center | Commercial | CMAR | Unknown | Active | Closeout | 36594000 | 37286000 | 36585500 | 36143900 | 44424800 | 98.8 | 2026-01-07 | 2026-02-24 | 1781600 | 1631500 | 692000 | 261800 | 21 | 13.8095 | 15 | 0.8136 | 0.98793 | -8280900 | -441600 | 44978022.0507 | 553222.0507 | -8384022.0507 | 22.91% | 1.891% | 48 | 1.891% | 0.7154% | 91.57% | 0.92687 | 71.43% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 90%
7 | PRJ-064 | Evergreen Townhomes | Residential | Design-Build | Unit Price | Complete | Closeout | 9022900 | 9260200 | 9022900 | 9022900 | 11060300 | 100 | 2024-04-15 | 2024-05-19 | 537500 | 496900 | 237300 | 74300 | 16 | 13.125 | 11 | 0.81579 | 1 | -2037400 | 0 | 11060300 | 0 | -2037400 | 22.58% | 2.63% | 34 | 2.63% | 0.8235% | 92.45% | 0.92447 | 68.75% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 90%
8 | PRJ-013 | Sunrise Housing | Residential | Design-Bid-Build | Cost Plus | Complete | Closeout | 9869600 | 10215500 | 9869600 | 9869600 | 12046900 | 100 | 2024-05-11 | 2024-07-11 | 609900 | 559400 | 345900 | 37400 | 20 | 18.5 | 19 | 0.81926 | 1 | -2177300 | 0 | 12046900 | 0 | -2177300 | 22.06% | 3.505% | 61 | 3.505% | 0.3789% | 91.72% | 0.9172 | 95% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 90%
9 | PRJ-069 | Cedar Valley Town Center | Mixed-Use | Design-Bid-Build | Unit Price | Active | Construction | 161964100 | 168322000 | 125005400 | 105957600 | 124778800 | 65.4 | 2026-08-14 | 2026-11-26 | 13234300 | 8089000 | 6357900 | 0 | 27 | 18.2222 | 22 | 0.84916 | 0.84762 | -18821200 | -19047800 | 190733708.9655 | 65954908.9655 | -28769608.9655 | 17.76% | 3.925% | 104 | 3.925% | 0% | 61.12% | 0.93458 | 81.48% | Red | CPI < 0.90 | CPI < 0.90; SPI < 0.90; Forecast overrun > 10%; Delay > 30 days
10 | PRJ-025 | Blue Mesa Public Safety Center | Institutional | CMAR | Cost Plus | Active | Procurement | 21839800 | 22229200 | 10668500 | 9269500 | 10383500 | 42.4 | 2027-04-08 | 2027-07-04 | 1701300 | 562200 | 389400 | 382800 | 23 | 17 | 18 | 0.89271 | 0.86887 | -1114000 | -1399000 | 24464487.1137 | 14080987.1137 | -2624687.1137 | 12.02% | 1.783% | 87 | 1.783% | 1.753% | 33.05% | 0.77937 | 78.26% | Red | CPI < 0.90 | CPI < 0.90; SPI < 0.90; Forecast overrun > 10%; Delay > 30 days
11 | PRJ-014 | Mountain Gate Bridge Rehabilitation | Heavy Civil & Infrastructure | Design-Build | Unit Price | Active | Construction | 102493600 | 105736500 | 96470100 | 90484300 | 112385400 | 88.3 | 2026-05-10 | 2026-07-23 | 7725500 | 5901700 | 3242900 | 0 | 22 | 18.5455 | 19 | 0.80513 | 0.93795 | -21901100 | -5985800 | 127301468.138 | 14916068.138 | -24807868.138 | 24.2% | 3.164% | 74 | 3.164% | 0% | 76.39% | 0.86515 | 86.36% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; SPI < 0.95; Contingency used > 75%
12 | PRJ-024 | Northstar Technology Facility | Industrial | Design-Bid-Build | Unit Price | Active | Construction | 172542200 | 179412400 | 164114100 | 155101100 | 191733000 | 89.9 | 2026-03-14 | 2026-04-26 | 8046600 | 7022000 | 6870200 | 478700 | 25 | 18.6 | 23 | 0.80894 | 0.94508 | -36631900 | -9013000 | 213293352.7396 | 21560352.7396 | -40751152.7396 | 23.62% | 3.982% | 43 | 3.982% | 0.2774% | 87.27% | 0.97071 | 92% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; SPI < 0.95; Contingency used > 75%
13 | PRJ-030 | Wasatch View Town Center | Mixed-Use | Design-Bid-Build | Unit Price | Complete | Closeout | 253200300 | 259343000 | 253200300 | 253200300 | 306003100 | 100 | 2025-09-19 | 2025-12-22 | 12089600 | 9983000 | 6142700 | 4495600 | 24 | 15.625 | 20 | 0.82744 | 1 | -52802800 | 0 | 306003100 | 0 | -52802800 | 20.85% | 2.426% | 94 | 2.426% | 1.776% | 82.58% | 0.82575 | 83.33% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 75%
14 | PRJ-038 | Mountain Gate Business Park | Commercial | Integrated Project Delivery | Unit Price | Complete | Closeout | 22273300 | 22592200 | 22273300 | 22273300 | 26865200 | 100 | 2024-02-15 | 2024-05-26 | 1367500 | 1045900 | 318900 | 155600 | 20 | 15 | 16 | 0.82908 | 1 | -4591900 | 0 | 26865200 | 0 | -4591900 | 20.62% | 1.432% | 101 | 1.432% | 0.6986% | 76.48% | 0.76483 | 80% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 75%
15 | PRJ-056 | Evergreen Medical Center | Institutional | Design-Bid-Build | Lump Sum | Complete | Closeout | 32329300 | 33008800 | 32329300 | 32329300 | 38880700 | 100 | 2024-02-18 | 2024-04-03 | 2313900 | 1903000 | 681400 | 275300 | 19 | 14.7895 | 15 | 0.8315 | 1 | -6551400 | 0 | 38880700 | 0 | -6551400 | 20.26% | 2.102% | 45 | 2.108% | 0.8515% | 82.24% | 0.82242 | 78.95% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 75%
16 | PRJ-067 | Wasatch View Retail Center | Commercial | Integrated Project Delivery | Cost Plus | Complete | Closeout | 43895700 | 44964800 | 43895700 | 43895700 | 52640800 | 100 | 2025-09-20 | 2025-10-30 | 3817000 | 3325900 | 1069100 | 477300 | 20 | 13.85 | 14 | 0.83387 | 1 | -8745100 | 0 | 52640800 | 0 | -8745100 | 19.92% | 2.436% | 40 | 2.436% | 1.087% | 87.13% | 0.87134 | 70% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 75%
17 | PRJ-074 | Evergreen Civic Center | Institutional | Design-Bid-Build | Cost Plus | Complete | Closeout | 65376400 | 67923400 | 65376400 | 65376400 | 77449800 | 100 | 2024-09-05 | 2024-11-22 | 4502800 | 3787500 | 2547000 | 88000 | 21 | 15.7619 | 17 | 0.84411 | 1 | -12073400 | 0 | 77449800 | 0 | -12073400 | 18.47% | 3.896% | 78 | 3.896% | 0.1346% | 84.11% | 0.84114 | 80.95% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 75%
18 | PRJ-060 | Mesa Vista Office Center | Commercial | Design-Build | Lump Sum | Complete | Closeout | 20440400 | 20956500 | 20440400 | 20440400 | 24131000 | 100 | 2024-02-07 | 2024-04-13 | 1974100 | 1469000 | 519800 | 15500 | 15 | 14.5333 | 10 | 0.84706 | 1 | -3690600 | 0 | 24131000 | 0 | -3690600 | 18.06% | 2.525% | 66 | 2.543% | 0.07583% | 74.41% | 0.74414 | 66.67% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days
19 | PRJ-062 | Riverbend Distribution Center | Industrial | Design-Bid-Build | Lump Sum | Active | Procurement | 56681500 | 57822100 | 27142400 | 25082900 | 29579800 | 44.3 | 2027-07-01 | 2027-08-26 | 3485200 | 1581700 | 1140600 | 1602500 | 24 | 17.5 | 19 | 0.84797 | 0.92412 | -4496900 | -2059500 | 66843444.4861 | 37263644.4861 | -10161944.4861 | 17.93% | 2.012% | 56 | 2.012% | 2.827% | 45.38% | 1.0245 | 79.17% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; SPI < 0.95
20 | PRJ-032 | Silver Lake Distribution Center | Industrial | Design-Build | Guaranteed Maximum Price | Complete | Closeout | 166470500 | 176506400 | 166470500 | 166470500 | 195288100 | 100 | 2025-04-16 | 2025-06-13 | 10548900 | 8023600 | 10035900 | 248300 | 17 | 13.4706 | 13 | 0.85244 | 1 | -28817600 | 0 | 195288100 | 0 | -28817600 | 17.31% | 6.029% | 58 | 6.029% | 0.1492% | 76.06% | 0.76061 | 76.47% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 75%
21 | PRJ-020 | Granite Peak Housing | Residential | Design-Build | Unknown | Complete | Closeout | 35061100 | 35288000 | 35061100 | 35061100 | 40963700 | 100 | 2025-08-16 | 2025-09-26 | 3074600 | 2444400 | 226900 | 534300 | 24 | 13.75 | 17 | 0.85591 | 1 | -5902600 | 0 | 40963700 | 0 | -5902600 | 16.84% | 0.6472% | 41 | 0.6472% | 1.524% | 79.5% | 0.79503 | 70.83% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 75%
22 | PRJ-004 | Red Rock Urban Village | Mixed-Use | Design-Bid-Build | Lump Sum | Complete | Closeout | 118914500 | 122268000 | 118914500 | 118914500 | 138905600 | 100 | 2025-01-19 | 2025-03-08 | 6654300 | 5132500 | 3353500 | 0 | 22 | 13.7727 | 16 | 0.85608 | 1 | -19991100 | 0 | 138905600 | 0 | -19991100 | 16.81% | 2.82% | 48 | 2.82% | 0% | 77.13% | 0.77131 | 72.73% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 75%
23 | PRJ-002 | Westfield Town Center | Mixed-Use | CMAR | Guaranteed Maximum Price | Complete | Closeout | 212894800 | 221375700 | 212894800 | 212894800 | 248382500 | 100 | 2024-05-17 | 2024-07-25 | 11291700 | 8462500 | 8480900 | 1563700 | 18 | 15.1667 | 16 | 0.85712 | 1 | -35487700 | 0 | 248382500 | 0 | -35487700 | 16.67% | 3.984% | 69 | 3.984% | 0.7345% | 74.94% | 0.74944 | 88.89% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days
24 | PRJ-040 | Silver Lake Learning Center | Institutional | Design-Build | Unit Price | Complete | Closeout | 92261500 | 93973600 | 92261500 | 92261500 | 107627000 | 100 | 2025-06-17 | 2025-08-23 | 5190200 | 3965200 | 1712100 | 0 | 22 | 13.2727 | 13 | 0.85723 | 1 | -15365500 | 0 | 107627000 | 0 | -15365500 | 16.65% | 1.856% | 67 | 1.856% | 0% | 76.4% | 0.76398 | 59.09% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 75%
25 | PRJ-070 | Wasatch View Main Street Development | Mixed-Use | Design-Build | Guaranteed Maximum Price | Active | Construction | 245591800 | 247663800 | 230300000 | 220550300 | 256495600 | 89.8 | 2026-06-11 | 2026-08-11 | 20109300 | 14832300 | 2072000 | 1629300 | 22 | 15.6818 | 16 | 0.85986 | 0.95767 | -35945300 | -9749700 | 285618365.0445 | 29122765.0445 | -40026565.0445 | 16.3% | 0.8437% | 61 | 0.8437% | 0.6634% | 73.76% | 0.82136 | 72.73% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days
26 | PRJ-053 | Summit Point Bridge Rehabilitation | Heavy Civil & Infrastructure | Design-Build | Lump Sum | Active | Closeout | 125893400 | 130412400 | 125892600 | 124993400 | 145003800 | 99.3 | 2026-01-01 | 2026-02-04 | 10257700 | 8276000 | 4519000 | 555200 | 20 | 15.05 | 14 | 0.862 | 0.99286 | -20010400 | -899200 | 146047882.4876 | 1044082.4876 | -20154482.4876 | 16.01% | 3.59% | 34 | 3.59% | 0.441% | 80.68% | 0.8125 | 70% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 75%
27 | PRJ-018 | Summit Point Retail Center | Commercial | Design-Build | Lump Sum | Complete | Closeout | 86603400 | 89995700 | 86603400 | 86603400 | 99602900 | 100 | 2025-02-18 | 2025-04-24 | 5291900 | 3646200 | 3392300 | 0 | 26 | 16.8846 | 22 | 0.86949 | 1 | -12999500 | 0 | 99602900 | 0 | -12999500 | 15.01% | 3.917% | 65 | 3.917% | 0% | 68.9% | 0.68902 | 84.62% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days
28 | PRJ-061 | Riverbend Business Park | Commercial | Design-Build | Guaranteed Maximum Price | Complete | Closeout | 50400400 | 52995000 | 50400400 | 50400400 | 57773800 | 100 | 2024-04-15 | 2024-05-29 | 3036000 | 2290100 | 2594600 | 142200 | 21 | 15.2857 | 18 | 0.87237 | 1 | -7373400 | 0 | 57773800 | 0 | -7373400 | 14.63% | 5.148% | 44 | 5.148% | 0.2821% | 75.43% | 0.75431 | 85.71% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 75%
29 | PRJ-063 | Copper Creek Water Program | Heavy Civil & Infrastructure | Integrated Project Delivery | Cost Plus | Active | Construction | 260432500 | 271624500 | 210698400 | 201803900 | 229839300 | 77.5 | 2026-09-04 | 2026-10-09 | 23076800 | 15551100 | 11192000 | 377800 | 24 | 15.5833 | 20 | 0.87802 | 0.95779 | -28035400 | -8894500 | 296612818.1727 | 66773518.1727 | -36180318.1727 | 13.89% | 4.297% | 35 | 4.297% | 0.1451% | 67.39% | 0.86953 | 83.33% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days
30 | PRJ-027 | Pioneer Crossing Market Hall | Commercial | Integrated Project Delivery | Unit Price | Active | Construction | 17917700 | 18159800 | 16350100 | 15610700 | 17742500 | 87.1 | 2026-05-13 | 2026-06-22 | 846000 | 556400 | 242100 | 133500 | 16 | 15.875 | 14 | 0.87985 | 0.95478 | -2131800 | -739400 | 20364544.335 | 2622044.335 | -2446844.335 | 13.66% | 1.351% | 40 | 1.351% | 0.7451% | 65.77% | 0.75509 | 87.5% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days
31 | PRJ-035 | Copper Creek Transit-Oriented Development | Mixed-Use | Design-Bid-Build | Lump Sum | Complete | Closeout | 159465200 | 161802600 | 159465200 | 159465200 | 180980800 | 100 | 2024-09-13 | 2024-11-02 | 7279100 | 5005700 | 2337400 | 0 | 25 | 16.36 | 21 | 0.88112 | 1 | -21515600 | 0 | 180980800 | 0 | -21515600 | 13.49% | 1.466% | 50 | 1.466% | 0% | 68.77% | 0.68768 | 84% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days
32 | PRJ-065 | Pioneer Crossing Logistics Hub | Industrial | Design-Build | Unit Price | Complete | Closeout | 105687000 | 108219700 | 105687000 | 105687000 | 119776500 | 100 | 2023-11-09 | 2024-01-06 | 9067800 | 5734500 | 2532700 | 120000 | 19 | 16.5789 | 15 | 0.88237 | 1 | -14089500 | 0 | 119776500 | 0 | -14089500 | 13.33% | 2.396% | 58 | 2.396% | 0.1135% | 63.24% | 0.6324 | 78.95% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days
33 | PRJ-043 | Copper Creek Logistics Hub | Industrial | CMAR | Cost Plus | Complete | Closeout | 249765500 | 259244400 | 249765500 | 249765500 | 279794600 | 100 | 2025-06-14 | 2025-07-22 | 24582100 | 18887900 | 9478900 | 0 | 21 | 14.619 | 16 | 0.89267 | 1 | -30029100 | 0 | 279794600 | 0 | -30029100 | 12.02% | 3.795% | 38 | 3.795% | 0% | 76.84% | 0.76836 | 76.19% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 75%
34 | PRJ-039 | Riverbend Civic Center | Institutional | CMAR | Unit Price | Complete | Closeout | 37607400 | 38041300 | 37607400 | 37607400 | 42019900 | 100 | 2024-02-17 | 2024-04-04 | 3050400 | 1597400 | 433900 | 233200 | 26 | 13.3462 | 19 | 0.89499 | 1 | -4412500 | 0 | 42019900 | 0 | -4412500 | 11.73% | 1.154% | 47 | 1.154% | 0.6201% | 52.37% | 0.52367 | 73.08% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days
35 | PRJ-058 | Silver Lake Civic Center | Institutional | Design-Bid-Build | Lump Sum | Complete | Closeout | 44536700 | 45550800 | 44536700 | 44536700 | 49738600 | 100 | 2025-07-11 | 2025-09-04 | 4216600 | 2742700 | 1014100 | 605200 | 13 | 15.0769 | 10 | 0.89542 | 1 | -5201900 | 0 | 49738600 | 0 | -5201900 | 11.68% | 2.277% | 55 | 2.277% | 1.359% | 65.05% | 0.65045 | 76.92% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days
36 | PRJ-003 | Mountain Gate Living Community | Residential | Design-Build | Guaranteed Maximum Price | Complete | Closeout | 55221600 | 56325600 | 55221600 | 55221600 | 61577600 | 100 | 2025-03-11 | 2025-04-22 | 3875600 | 2292100 | 1104000 | 0 | 17 | 15.4706 | 14 | 0.89678 | 1 | -6356000 | 0 | 61577600 | 0 | -6356000 | 11.51% | 1.999% | 42 | 1.999% | 0% | 59.14% | 0.59142 | 82.35% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days
37 | PRJ-072 | Riverbend Residences | Residential | CMAR | Cost Plus | Complete | Closeout | 49424500 | 50333400 | 49424500 | 49424500 | 55077200 | 100 | 2024-08-13 | 2024-10-02 | 3642300 | 2167900 | 908900 | 306800 | 20 | 16.15 | 17 | 0.89737 | 1 | -5652700 | 0 | 55077200 | 0 | -5652700 | 11.44% | 1.839% | 50 | 1.839% | 0.6207% | 59.52% | 0.5952 | 85% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days
38 | PRJ-016 | Canyon Ridge Processing Plant | Industrial | Design-Build | Lump Sum | Complete | Closeout | 56509100 | 56919400 | 56509100 | 56509100 | 68477200 | 100 | 2023-03-17 | 2023-03-28 | 5602900 | 4581200 | 410300 | 941700 | 22 | 16 | 17 | 0.82523 | 1 | -11968100 | 0 | 68477200 | 0 | -11968100 | 21.18% | 0.7261% | 11 | 0.7261% | 1.666% | 81.76% | 0.81765 | 77.27% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Contingency used > 75%
39 | PRJ-031 | Canyon Ridge Medical Center | Institutional | CMAR | Guaranteed Maximum Price | Complete | Closeout | 15252700 | 15359400 | 15252700 | 15252700 | 18410900 | 100 | 2024-05-13 | 2024-06-07 | 1074000 | 944100 | 106700 | 242300 | 27 | 15.3704 | 21 | 0.82846 | 1 | -3158200 | 0 | 18410900 | 0 | -3158200 | 20.71% | 0.6995% | 25 | 0.6995% | 1.589% | 87.91% | 0.87905 | 77.78% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 15 days; Contingency used > 75%
40 | PRJ-008 | Northstar Community College | Institutional | Design-Bid-Build | Lump Sum | Complete | Closeout | 122227200 | 127351100 | 122227200 | 122227200 | 144902900 | 100 | 2025-07-07 | 2025-07-30 | 6535400 | 5522200 | 5123900 | 0 | 24 | 14 | 18 | 0.84351 | 1 | -22675700 | 0 | 144902900 | 0 | -22675700 | 18.55% | 4.192% | 23 | 4.192% | 0% | 84.5% | 0.84497 | 75% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 15 days; Contingency used > 75%
41 | PRJ-042 | Northstar Corporate Campus | Commercial | Design-Build | Cost Plus | Complete | Closeout | 8337500 | 8438700 | 8337500 | 8337500 | 9359700 | 100 | 2023-10-13 | 2023-10-13 | 494500 | 344100 | 101200 | 0 | 21 | 12.2381 | 14 | 0.89079 | 1 | -1022200 | 0 | 9359700 | 0 | -1022200 | 12.26% | 1.214% | 0 | 1.214% | 0% | 69.59% | 0.69585 | 66.67% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%
42 | PRJ-007 | Granite Peak Apartments | Residential | Design-Bid-Build | Guaranteed Maximum Price | Complete | Closeout | 29562600 | 30109700 | 29562600 | 29562600 | 32982900 | 100 | 2025-06-02 | 2025-06-18 | 1625900 | 1130900 | 547100 | 0 | 20 | 15.05 | 15 | 0.8963 | 1 | -3420300 | 0 | 32982900 | 0 | -3420300 | 11.57% | 1.851% | 16 | 1.851% | 0% | 69.56% | 0.69555 | 75% | Red | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 15 days
43 | PRJ-022 | Summit Point Public Safety Center | Institutional | Design-Build | Guaranteed Maximum Price | Active | Construction | 64744000 | 65132800 | 46320500 | 42694600 | 47060000 | 65.9 | 2026-09-14 | 2026-11-01 | 3915700 | 1815600 | 388800 | 810700 | 21 | 15.4286 | 16 | 0.90724 | 0.92172 | -4365400 | -3625900 | 71363887.7048 | 24303887.7048 | -6619887.7048 | 10.22% | 0.6005% | 48 | 0.6005% | 1.252% | 46.37% | 0.7036 | 76.19% | Red | Forecast overrun > 10% | Forecast overrun > 10%; Delay > 30 days; CPI < 0.95; SPI < 0.95
44 | PRJ-006 | Red Rock Bridge Rehabilitation | Heavy Civil & Infrastructure | Design-Bid-Build | Unit Price | Complete | Closeout | 36211800 | 36646600 | 36211800 | 36211800 | 39996600 | 100 | 2024-09-05 | 2024-09-15 | 1839800 | 1219300 | 434800 | 0 | 19 | 14.6842 | 16 | 0.90537 | 1 | -3784800 | 0 | 39996600 | 0 | -3784800 | 10.45% | 1.201% | 10 | 1.201% | 0% | 66.27% | 0.66274 | 84.21% | Red | Forecast overrun > 10% | Forecast overrun > 10%; CPI < 0.95
45 | PRJ-011 | Westfield Housing | Residential | Design-Bid-Build | Guaranteed Maximum Price | Complete | Closeout | 27228800 | 27507400 | 27228800 | 27228800 | 30047900 | 100 | 2023-12-14 | 2024-01-13 | 2455500 | 1469100 | 278600 | 131900 | 22 | 14.0455 | 18 | 0.90618 | 1 | -2819100 | 0 | 30047900 | 0 | -2819100 | 10.35% | 1.023% | 30 | 1.023% | 0.4844% | 59.83% | 0.59829 | 81.82% | Red | Forecast overrun > 10% | Forecast overrun > 10%; CPI < 0.95; Delay > 15 days
46 | PRJ-028 | Evergreen Residences | Residential | Design-Bid-Build | Cost Plus | Complete | Closeout | 9052000 | 9293400 | 9052000 | 9052000 | 9795600 | 100 | 2023-12-01 | 2024-01-05 | 604800 | 326700 | 241400 | 30400 | 18 | 13.5 | 15 | 0.92409 | 1 | -743600 | 0 | 9795600 | 0 | -743600 | 8.215% | 2.667% | 35 | 2.667% | 0.3358% | 54.02% | 0.54018 | 83.33% | Red | Delay > 30 days | Delay > 30 days; CPI < 0.95; Forecast overrun > 5%
47 | PRJ-071 | Canyon Ridge Public Safety Center | Institutional | Design-Bid-Build | Guaranteed Maximum Price | Active | Construction | 129697800 | 134156200 | 117545300 | 107815700 | 116074200 | 83.1 | 2026-05-18 | 2026-07-28 | 6602300 | 3453400 | 4458400 | 0 | 25 | 11.2 | 17 | 0.92885 | 0.91723 | -8258500 | -9729600 | 139632431.7957 | 23558231.7957 | -9934631.7957 | 7.66% | 3.438% | 71 | 3.438% | 0% | 52.31% | 0.62943 | 68% | Red | Delay > 30 days | Delay > 30 days; CPI < 0.95; SPI < 0.95; Forecast overrun > 5%
48 | PRJ-001 | Desert Willow Public Safety Center | Institutional | CMAR | Lump Sum | Active | Closeout | 47876900 | 48500200 | 47876900 | 47666400 | 51257800 | 99.6 | 2025-12-09 | 2026-01-23 | 2996700 | 1708600 | 623300 | 0 | 17 | 13.2941 | 12 | 0.92993 | 0.9956 | -3591400 | -210500 | 51484160.0125 | 226360.0125 | -3607260.0125 | 7.534% | 1.302% | 45 | 1.302% | 0% | 57.02% | 0.57245 | 70.59% | Red | Delay > 30 days | Delay > 30 days; CPI < 0.95; Forecast overrun > 5%
49 | PRJ-057 | Highland Park Medical Center | Institutional | Design-Bid-Build | Unit Price | Active | Closeout | 49732600 | 50949700 | 49732600 | 49054700 | 51228200 | 98.6 | 2025-12-16 | 2026-02-22 | 3172800 | 1934900 | 1217100 | 325000 | 19 | 12.4211 | 13 | 0.95757 | 0.98637 | -2173500 | -677900 | 51936136.177 | 707936.177 | -2203536.177 | 4.431% | 2.447% | 68 | 2.447% | 0.6535% | 60.98% | 0.6185 | 68.42% | Red | Delay > 30 days | Delay > 30 days
50 | PRJ-023 | Blue Mesa Medical Center | Institutional | Design-Build | Guaranteed Maximum Price | Active | Construction | 53214100 | 55945100 | 39708000 | 36619000 | 38106600 | 68.8 | 2026-11-17 | 2027-01-22 | 4374600 | 2038800 | 2731000 | 321200 | 22 | 9.8182 | 9 | 0.96096 | 0.92221 | -1487600 | -3089000 | 55375854.6946 | 17269254.6946 | -2161754.6946 | 4.062% | 5.132% | 66 | 5.132% | 0.6036% | 46.61% | 0.6774 | 40.91% | Red | Delay > 30 days | Delay > 30 days; SPI < 0.95
51 | PRJ-041 | Westfield Residences | Residential | Integrated Project Delivery | Guaranteed Maximum Price | Complete | Closeout | 39698700 | 40381800 | 39698700 | 39698700 | 43666000 | 100 | 2024-11-09 | 2024-11-11 | 3209000 | 2108100 | 683100 | 523400 | 16 | 12.6875 | 9 | 0.90914 | 1 | -3967300 | 0 | 43666000 | 0 | -3967300 | 9.994% | 1.721% | 2 | 1.721% | 1.318% | 65.69% | 0.65693 | 56.25% | Yellow | CPI < 0.95 | CPI < 0.95; Forecast overrun > 5%
52 | PRJ-066 | Aspen Grove Medical Center | Institutional | Design-Bid-Build | Lump Sum | Active | Closeout | 34715500 | 35038500 | 33235100 | 32652600 | 35828600 | 94.1 | 2026-05-05 | 2026-06-02 | 2142000 | 1335700 | 323000 | 187300 | 13 | 13.0769 | 10 | 0.91136 | 0.98247 | -3176000 | -582500 | 38092150.8027 | 2263550.8027 | -3376650.8027 | 9.727% | 0.9304% | 28 | 0.9304% | 0.5395% | 62.36% | 0.66267 | 76.92% | Yellow | CPI < 0.95 | CPI < 0.95; Forecast overrun > 5%; Delay > 15 days
53 | PRJ-050 | Copper Creek Mixed-Use District | Mixed-Use | Design-Bid-Build | Guaranteed Maximum Price | Active | Closeout | 67108500 | 68117300 | 65489800 | 64511400 | 70784800 | 96.1 | 2026-03-17 | 2026-04-10 | 5408000 | 2833500 | 1008800 | 119800 | 17 | 14.4706 | 11 | 0.91137 | 0.98506 | -6273400 | -978400 | 73634454.5429 | 2849654.5429 | -6525954.5429 | 9.724% | 1.503% | 24 | 1.503% | 0.1785% | 52.39% | 0.54521 | 64.71% | Yellow | CPI < 0.95 | CPI < 0.95; Forecast overrun > 5%; Delay > 15 days
54 | PRJ-055 | Sunrise Market Hall | Commercial | Design-Bid-Build | Lump Sum | Complete | Closeout | 30802600 | 31227600 | 30802600 | 30802600 | 33743900 | 100 | 2022-10-16 | 2022-11-06 | 2330000 | 1360300 | 425000 | 0 | 22 | 15.4545 | 19 | 0.91283 | 1 | -2941300 | 0 | 33743900 | 0 | -2941300 | 9.549% | 1.38% | 21 | 1.38% | 0% | 58.38% | 0.58382 | 86.36% | Yellow | CPI < 0.95 | CPI < 0.95; Forecast overrun > 5%; Delay > 15 days
55 | PRJ-049 | Red Rock Business Park | Commercial | CMAR | Guaranteed Maximum Price | Complete | Closeout | 5632400 | 5753800 | 5632400 | 5632400 | 6131200 | 100 | 2024-10-10 | 2024-10-20 | 322500 | 195300 | 121400 | 0 | 15 | 12 | 11 | 0.91865 | 1 | -498800 | 0 | 6131200 | 0 | -498800 | 8.856% | 2.155% | 10 | 2.155% | 0% | 60.56% | 0.60558 | 73.33% | Yellow | CPI < 0.95 | CPI < 0.95; Forecast overrun > 5%
56 | PRJ-047 | Northstar Roadway Improvements | Heavy Civil & Infrastructure | CMAR | Unit Price | Complete | Closeout | 65704000 | 65704000 | 65679000 | 65704000 | 71351900 | 100 | 2025-05-11 | 2025-04-27 | 4972500 | 2783800 | 0 | 641000 | 17 | 14.6471 | 14 | 0.92084 | 1.0004 | -5647900 | 25000 | 71351900 | 0 | -5647900 | 8.596% | 0% | -14 | 0% | 0.9756% | 55.98% | 0.55984 | 82.35% | Yellow | CPI < 0.95 | CPI < 0.95; Forecast overrun > 5%
57 | PRJ-036 | Canyon Ridge Residences | Residential | Design-Build | Unit Price | Active | Construction | 13348200 | 13714700 | 9954800 | 9629800 | 10410300 | 72.1 | 2026-09-18 | 2026-10-10 | 1050300 | 559200 | 366500 | 0 | 20 | 15.2 | 15 | 0.92503 | 0.96735 | -780500 | -325000 | 14430078.1387 | 4019778.1387 | -1081878.1387 | 8.105% | 2.746% | 22 | 2.746% | 0% | 53.24% | 0.73845 | 75% | Yellow | CPI < 0.95 | CPI < 0.95; Forecast overrun > 5%; Delay > 15 days
58 | PRJ-037 | Red Rock Townhomes | Residential | CMAR | Guaranteed Maximum Price | Complete | Closeout | 81557700 | 82209900 | 81557700 | 81557700 | 87724100 | 100 | 2025-01-10 | 2025-01-23 | 8071900 | 5131900 | 652200 | 843200 | 16 | 13.3125 | 12 | 0.92971 | 1 | -6166400 | 0 | 87724100 | 0 | -6166400 | 7.561% | 0.7997% | 13 | 0.7997% | 1.034% | 63.58% | 0.63577 | 75% | Yellow | CPI < 0.95 | CPI < 0.95; Forecast overrun > 5%
59 | PRJ-044 | Canyon Ridge Urban Village | Mixed-Use | Design-Build | Lump Sum | Active | Procurement | 79900800 | 81018700 | 31886300 | 30642500 | 32731600 | 38.4 | 2027-08-10 | 2027-09-05 | 6493900 | 1619000 | 1117900 | 857100 | 15 | 13.2667 | 11 | 0.93617 | 0.96099 | -2089100 | -1243800 | 85348161.06 | 52616561.06 | -5447361.06 | 6.818% | 1.399% | 26 | 1.399% | 1.073% | 24.93% | 0.64925 | 73.33% | Yellow | CPI < 0.95 | CPI < 0.95; Forecast overrun > 5%; Delay > 15 days
60 | PRJ-005 | Pioneer Crossing Living Community | Residential | Design-Bid-Build | Lump Sum | Complete | Closeout | 76603500 | 77653900 | 76603000 | 76603500 | 81439200 | 100 | 2024-09-01 | 2024-08-29 | 4401700 | 2202900 | 1050400 | 724700 | 13 | 12.6923 | 10 | 0.94062 | 1 | -4835700 | 500 | 81439200 | 0 | -4835700 | 6.313% | 1.371% | -3 | 1.371% | 0.946% | 50.05% | 0.50047 | 76.92% | Yellow | CPI < 0.95 | CPI < 0.95; Forecast overrun > 5%
61 | PRJ-054 | Evergreen Corporate Campus | Commercial | CMAR | Guaranteed Maximum Price | Complete | Closeout | 84587500 | 85582600 | 84587500 | 84587500 | 89081600 | 100 | 2024-03-15 | 2024-04-08 | 4106100 | 1881600 | 995100 | 1628200 | 12 | 11 | 7 | 0.94955 | 1 | -4494100 | 0 | 89081600 | 0 | -4494100 | 5.313% | 1.176% | 24 | 1.176% | 1.925% | 45.82% | 0.45825 | 58.33% | Yellow | CPI < 0.95 | CPI < 0.95; Forecast overrun > 5%; Delay > 15 days
62 | PRJ-012 | Cedar Valley Processing Plant | Industrial | Design-Bid-Build | Cost Plus | Complete | Closeout | 23128700 | 23520900 | 23128400 | 23128700 | 24331800 | 100 | 2025-06-02 | 2025-05-24 | 1511200 | 964000 | 392200 | 0 | 17 | 15.2353 | 13 | 0.95055 | 1 | -1203100 | 300 | 24331800 | 0 | -1203100 | 5.202% | 1.696% | -9 | 1.696% | 0% | 63.79% | 0.6379 | 76.47% | Yellow | Forecast overrun > 5% | Forecast overrun > 5%
63 | PRJ-045 | Desert Willow Learning Center | Institutional | Design-Bid-Build | Unit Price | Complete | Closeout | 51862400 | 53099400 | 51862400 | 51862400 | 54328500 | 100 | 2025-08-12 | 2025-09-08 | 3380500 | 1617100 | 1237000 | 0 | 17 | 13.5294 | 12 | 0.95461 | 1 | -2466100 | 0 | 54328500 | 0 | -2466100 | 4.755% | 2.385% | 27 | 2.385% | 0% | 47.84% | 0.47836 | 70.59% | Yellow | Delay > 15 days | Delay > 15 days
64 | PRJ-033 | Copper Creek Utility Expansion | Heavy Civil & Infrastructure | Design-Bid-Build | Unit Price | Complete | Closeout | 297370800 | 305739600 | 297166200 | 297370800 | 312104000 | 100 | 2025-09-13 | 2025-08-14 | 28683800 | 18207900 | 8368800 | 644200 | 20 | 16.1 | 16 | 0.95279 | 1.0007 | -14733200 | 204600 | 312104000 | 0 | -14733200 | 4.954% | 2.814% | -30 | 2.814% | 0.2166% | 63.48% | 0.63478 | 80% | Green | No threshold breach | None
65 | PRJ-073 | Silver Lake Corporate Campus | Commercial | Design-Build | Unit Price | Complete | Closeout | 74572000 | 75370600 | 74387300 | 74572000 | 77377500 | 100 | 2025-05-15 | 2025-04-15 | 5524500 | 3493200 | 798600 | 0 | 18 | 14.6111 | 17 | 0.96374 | 1.0025 | -2805500 | 184700 | 77377500 | 0 | -2805500 | 3.762% | 1.071% | -30 | 1.071% | 0% | 63.23% | 0.63231 | 94.44% | Green | No threshold breach | None
66 | PRJ-052 | Cedar Valley Market Hall | Commercial | Design-Build | Guaranteed Maximum Price | Complete | Closeout | 12129200 | 12238200 | 12129000 | 12129200 | 12578600 | 100 | 2025-06-02 | 2025-05-03 | 672600 | 385700 | 109000 | 94300 | 14 | 11.4286 | 8 | 0.96427 | 1 | -449400 | 200 | 12578600 | 0 | -449400 | 3.705% | 0.8987% | -30 | 0.8987% | 0.7775% | 57.34% | 0.57345 | 57.14% | Green | No threshold breach | None
67 | PRJ-015 | Summit Point Main Street Development | Mixed-Use | Design-Bid-Build | Guaranteed Maximum Price | Complete | Closeout | 60271400 | 60423500 | 60271400 | 60271400 | 62381500 | 100 | 2024-07-14 | 2024-07-10 | 4382900 | 2193500 | 152100 | 1985400 | 18 | 10.7778 | 12 | 0.96617 | 1 | -2110100 | 0 | 62381500 | 0 | -2110100 | 3.501% | 0.2524% | -4 | 0.2524% | 3.294% | 50.05% | 0.50047 | 66.67% | Green | No threshold breach | None
68 | PRJ-059 | Westfield Community College | Institutional | CMAR | Unit Price | Active | Procurement | 36111700 | 36561800 | 15070800 | 15166100 | 15685100 | 42 | 2027-07-11 | 2027-07-07 | 3303200 | 789200 | 450100 | 197400 | 25 | 12.68 | 16 | 0.96691 | 1.0063 | -519000 | 95300 | 37347480.6094 | 21662380.6094 | -1235780.6094 | 3.422% | 1.246% | -4 | 1.246% | 0.5466% | 23.89% | 0.56886 | 64% | Green | No threshold breach | None
69 | PRJ-026 | Pioneer Crossing Distribution Center | Industrial | Design-Build | Guaranteed Maximum Price | Active | Construction | 45993600 | 46567600 | 35438200 | 35181700 | 35953800 | 76.5 | 2026-09-03 | 2026-09-08 | 4019900 | 1731100 | 574000 | 184200 | 20 | 12.6 | 14 | 0.97853 | 0.99276 | -772100 | -256500 | 47002978.6986 | 11049178.6986 | -1009378.6986 | 2.195% | 1.248% | 5 | 1.248% | 0.4005% | 43.06% | 0.56292 | 70% | Green | No threshold breach | None
70 | PRJ-019 | Copper Creek Learning Center | Institutional | Design-Bid-Build | Unknown | Active | Construction | 102004800 | 104613700 | 57629400 | 58175600 | 59010600 | 57 | 2026-12-13 | 2026-12-08 | 9598300 | 3569300 | 2608900 | 242900 | 17 | 11.4118 | 12 | 0.98585 | 1.0095 | -835000 | 546200 | 103468884.7366 | 44458284.7366 | -1464084.7366 | 1.435% | 2.558% | -5 | 2.558% | 0.2381% | 37.19% | 0.6524 | 70.59% | Green | No threshold breach | None
71 | PRJ-029 | Granite Peak Bridge Rehabilitation | Heavy Civil & Infrastructure | CMAR | Lump Sum | Active | Construction | 123914200 | 126668300 | 101631500 | 109145800 | 109804900 | 88.1 | 2026-09-12 | 2026-08-13 | 9348900 | 3996100 | 2754100 | 523200 | 19 | 13.2632 | 11 | 0.994 | 1.0739 | -659100 | 7514300 | 124662482.1072 | 14857582.1072 | -748282.1072 | 0.6039% | 2.223% | -30 | 2.223% | 0.4222% | 42.74% | 0.48518 | 57.89% | Green | No threshold breach | None
72 | PRJ-051 | Westfield Technology Facility | Industrial | Design-Build | Guaranteed Maximum Price | Complete | Closeout | 108544300 | 109327700 | 108478300 | 108544300 | 107577800 | 100 | 2023-07-10 | 2023-06-10 | 9834600 | 5035700 | 783400 | 562400 | 13 | 9.6923 | 6 | 1.009 | 1.0006 | 966500 | 66000 | 107577800 | 0 | 966500 | -0.8904% | 0.7217% | -30 | 0.7217% | 0.5181% | 51.2% | 0.51204 | 46.15% | Green | No threshold breach | None
73 | PRJ-010 | Silver Lake Bridge Rehabilitation | Heavy Civil & Infrastructure | CMAR | Lump Sum | Complete | Closeout | 115348100 | 116127800 | 115072600 | 115348100 | 113751100 | 100 | 2024-02-20 | 2024-01-21 | 9324700 | 4052400 | 779700 | 186900 | 19 | 11.5789 | 11 | 1.014 | 1.0024 | 1597000 | 275500 | 113751100 | 0 | 1597000 | -1.385% | 0.676% | -30 | 0.676% | 0.162% | 43.46% | 0.43459 | 57.89% | Green | No threshold breach | None
74 | PRJ-021 | Highland Park Roadway Improvements | Heavy Civil & Infrastructure | Design-Build | Guaranteed Maximum Price | Complete | Closeout | 67733200 | 68598600 | 67662700 | 67733200 | 66732300 | 100 | 2024-04-12 | 2024-03-22 | 6687100 | 3102400 | 865400 | 1012800 | 19 | 12.9474 | 12 | 1.015 | 1.001 | 1000900 | 70500 | 66732300 | 0 | 1000900 | -1.478% | 1.278% | -21 | 1.278% | 1.495% | 46.39% | 0.46394 | 63.16% | Green | No threshold breach | None
75 | PRJ-048 | Mesa Vista Urban Village | Mixed-Use | CMAR | Guaranteed Maximum Price | Complete | Closeout | 42336600 | 43200200 | 42306700 | 42336600 | 41410600 | 100 | 2024-05-15 | 2024-04-15 | 4226300 | 2109000 | 863600 | 0 | 22 | 9.3182 | 13 | 1.0224 | 1.0007 | 926000 | 29900 | 41410600 | 7.4506e-09 | 926000 | -2.187% | 2.04% | -30 | 2.04% | 0% | 49.9% | 0.49902 | 59.09% | Green | No threshold breach | None

## Project_Type
Performance by Project Type
Project_Type | Project_Count | Total_BAC | Weighted_CPI | Weighted_SPI | Forecast_Overrun_Pct | Average_Delay_Days | Median_Delay_Days | Average_Approved_CO_Pct | Average_RFI_Response_Days | Red_Project_Count | Red_Project_Rate
Commercial | 13 | 494186100 | 0.89115 | 0.99798 | 12.23% | 30.6923 | 40 | 2.047% | 13.9977 | 8 | 61.54%
Heavy Civil & Infrastructure | 10 | 1249468300 | 0.91629 | 0.99343 | 9.407% | 8.3 | -2 | 2.322% | 14.9496 | 5 | 50%
Industrial | 9 | 985322400 | 0.8793 | 0.98798 | 13.91% | 25.5556 | 38 | 2.512% | 14.9218 | 6 | 66.67%
Institutional | 18 | 1061372700 | 0.89159 | 0.98012 | 11.27% | 44.9444 | 46 | 2.336% | 13.7176 | 14 | 77.78%
Mixed-Use | 11 | 1506567600 | 0.85735 | 0.97773 | 16.34% | 46.8182 | 50 | 2.185% | 14.3862 | 7 | 63.64%
Residential | 14 | 534519500 | 0.87717 | 0.99939 | 13.96% | 35 | 34.5 | 2.064% | 14.8702 | 10 | 71.43%

## Delivery_Method
Performance by Delivery Method
Delivery_Method | Project_Count | Total_BAC | Weighted_CPI | Weighted_SPI | Forecast_Overrun_Pct | Average_Delay_Days | Median_Delay_Days | Average_Approved_CO_Pct | Average_RFI_Response_Days | Red_Project_Count | Red_Project_Rate
CMAR | 17 | 1286429700 | 0.91047 | 1.0048 | 9.649% | 22.7059 | 25 | 1.812% | 13.6468 | 9 | 52.94%
Design-Bid-Build | 28 | 2381747100 | 0.87634 | 0.98147 | 14.02% | 38 | 39 | 2.41% | 14.805 | 19 | 67.86%
Design-Build | 25 | 1779041900 | 0.87798 | 0.98506 | 13.59% | 34.32 | 42 | 2.316% | 14.3832 | 18 | 72%
Integrated Project Delivery | 5 | 384217900 | 0.87196 | 0.97106 | 14.56% | 43.6 | 40 | 2.247% | 14.5992 | 4 | 80%

## Contract_Type
Performance by Contract Type
Contract_Type | Project_Count | Total_BAC | Weighted_CPI | Weighted_SPI | Forecast_Overrun_Pct | Average_Delay_Days | Median_Delay_Days | Average_Approved_CO_Pct | Average_RFI_Response_Days | Red_Project_Count | Red_Project_Rate
Cost Plus | 10 | 741122200 | 0.88064 | 0.98487 | 13.55% | 41.5 | 39 | 2.713% | 15.2438 | 9 | 90%
Guaranteed Maximum Price | 23 | 1700467000 | 0.90375 | 0.98326 | 10.57% | 24.1739 | 24 | 2.047% | 13.2597 | 12 | 52.17%
Lump Sum | 18 | 1397035800 | 0.88843 | 1.0022 | 12.35% | 33 | 39.5 | 2.138% | 14.5858 | 12 | 66.67%
Unit Price | 20 | 1714232100 | 0.87236 | 0.97844 | 14.74% | 40.2 | 41.5 | 2.312% | 15.23 | 14 | 70%
Unknown | 4 | 278579500 | 0.82566 | 0.99918 | 18.03% | 39.25 | 44.5 | 2.117% | 13.6394 | 3 | 75%

## Correlations
Relationship Testing — Pearson Correlation
Relationship | X_Variable | Y_Variable | Pearson_r | R_Squared | Strength | Direction | Interpretation
Approved CO % vs Cost Growth % | Approved_CO_Pct | Cost_Growth_Pct | 0.99977 | 0.99955 | Strong | Positive | strong positive association; does not establish causation.
Approved CO % vs Forecast Overrun % | Approved_CO_Pct | Forecast_Overrun_Pct | 0.40047 | 0.16037 | Moderate | Positive | moderate positive association; does not establish causation.
Average RFI Response Days vs Schedule Delay Days | Avg_RFI_Response_Days | Schedule_Delay_Days | 0.51695 | 0.26723 | Moderate | Positive | moderate positive association; does not establish causation.
Late RFI Rate vs Schedule Delay Days | Late_RFI_Rate | Schedule_Delay_Days | 0.34281 | 0.11752 | Modest | Positive | modest positive association; does not establish causation.
Contingency Burn Ratio vs Forecast Overrun % | Contingency_Burn_Ratio | Forecast_Overrun_Pct | 0.90084 | 0.8115 | Strong | Positive | strong positive association; does not establish causation.
RFI Density vs Schedule Delay Days | RFI_per_10M | Schedule_Delay_Days | -0.057826 | 0.0033438 | Weak | Negative | weak negative association; does not establish causation.
CO Density vs Forecast Overrun % | CO_per_10M | Forecast_Overrun_Pct | 0.15211 | 0.023138 | Weak | Positive | weak positive association; does not establish causation.
Interpretation caution: Pearson correlation measures linear association, not causation. The near-perfect relationship between Approved CO % and Cost Growth % is definitional because Current Budget was constructed as Original Budget plus approved change orders. It is a data-model validation, not an independent business finding.

## Monthly_Trend
Monthly Portfolio Performance Trend
Reporting_Date | Reporting_Project_Count | Total_PV | Total_EV | Total_AC | Total_Contingency_Used | Total_Approved_CO_Value | Total_Pending_CO_Value | Weighted_CPI | Weighted_SPI | Reporting Date | Weighted CPI | Weighted SPI
2022-01-31 | 12 | 68918300 | 65318600 | 69611200 | 4982000 | 853800 | 249700 | 0.93833 | 0.94777 | 2022-01-31 | 0.93833 | 0.94777
2022-02-28 | 12 | 93272900 | 88288200 | 95549300 | 7194000 | 853800 | 270800 | 0.92401 | 0.94656 | 2022-02-28 | 0.92401 | 0.94656
2022-03-31 | 15 | 123806400 | 117117900 | 125526900 | 9965600 | 1783600 | 270800 | 0.93301 | 0.94598 | 2022-03-31 | 0.93301 | 0.94598
2022-04-30 | 16 | 157794700 | 149404900 | 161460200 | 12319600 | 1969100 | 319300 | 0.92534 | 0.94683 | 2022-04-30 | 0.92534 | 0.94683
2022-05-31 | 18 | 198445200 | 188124700 | 203010800 | 15171100 | 3005100 | 319300 | 0.92667 | 0.94799 | 2022-05-31 | 0.92667 | 0.94799
2022-06-30 | 20 | 243360700 | 230974100 | 251258700 | 17885500 | 3443500 | 471000 | 0.91927 | 0.9491 | 2022-06-30 | 0.91927 | 0.9491
2022-07-31 | 23 | 295805800 | 281094000 | 308427800 | 21168700 | 4048600 | 471000 | 0.91138 | 0.95027 | 2022-07-31 | 0.91138 | 0.95027
2022-08-31 | 26 | 354482400 | 338144600 | 373245100 | 23496900 | 4825300 | 2660200 | 0.90596 | 0.95391 | 2022-08-31 | 0.90596 | 0.95391
2022-09-30 | 28 | 417025100 | 399097300 | 440202950 | 26902900 | 6223200 | 2660200 | 0.90662 | 0.95701 | 2022-09-30 | 0.90662 | 0.95701
2022-10-31 | 32 | 487775300 | 468035500 | 511369900 | 30744000 | 8943100 | 2660200 | 0.91526 | 0.95953 | 2022-10-31 | 0.91526 | 0.95953
2022-11-30 | 33 | 564259400 | 541762100 | 591784100 | 34233300 | 9629200 | 2938200 | 0.91547 | 0.96013 | 2022-11-30 | 0.91547 | 0.96013
2022-12-31 | 33 | 619782200 | 594186000 | 648918900 | 39917100 | 11178400 | 3141200 | 0.91566 | 0.9587 | 2022-12-31 | 0.91566 | 0.9587
2023-01-31 | 33 | 712885800 | 684068600 | 748496300 | 43401000 | 11853400 | 3168100 | 0.91392 | 0.95958 | 2023-01-31 | 0.91392 | 0.95958
2023-02-28 | 36 | 801689700 | 770209700 | 839803100 | 47861700 | 13276000 | 3977600 | 0.91713 | 0.96073 | 2023-02-28 | 0.91713 | 0.96073
2023-03-31 | 37 | 905438300 | 869627000 | 955560600 | 50856900 | 15965200 | 4065600 | 0.91007 | 0.96045 | 2023-03-31 | 0.91007 | 0.96045
2023-04-30 | 40 | 954370900 | 913392400 | 997491900 | 53256000 | 16673700 | 3884000 | 0.91569 | 0.95706 | 2023-04-30 | 0.91569 | 0.95706
2023-05-31 | 42 | 1070882200 | 1024698400 | 1114951400 | 56178500 | 18068800 | 4528500 | 0.91905 | 0.95687 | 2023-05-31 | 0.91905 | 0.95687
2023-06-30 | 43 | 1191882500 | 1141037400 | 1245030700 | 62542300 | 18778700 | 4623800 | 0.91647 | 0.95734 | 2023-06-30 | 0.91647 | 0.95734
2023-07-31 | 42 | 1180844300 | 1125644300 | 1234139800 | 62236600 | 22114600 | 4383200 | 0.91209 | 0.95325 | 2023-07-31 | 0.91209 | 0.95325
2023-08-31 | 44 | 1319673600 | 1259958600 | 1380239600 | 67132100 | 23275500 | 4534600 | 0.91285 | 0.95475 | 2023-08-31 | 0.91285 | 0.95475
2023-09-30 | 44 | 1394755100 | 1331179800 | 1448309500 | 67063400 | 23178100 | 4486100 | 0.91913 | 0.95442 | 2023-09-30 | 0.91913 | 0.95442
2023-10-31 | 45 | 1541353900 | 1474218300 | 1605255100 | 72338600 | 23852800 | 5473700 | 0.91837 | 0.95644 | 2023-10-31 | 0.91837 | 0.95644
2023-11-30 | 45 | 1675281400 | 1603120500 | 1740530600 | 78329600 | 25040800 | 5473700 | 0.92105 | 0.95693 | 2023-11-30 | 0.92105 | 0.95693
2023-12-31 | 49 | 1821560600 | 1745583400 | 1910601100 | 88392300 | 28436000 | 5749000 | 0.91363 | 0.95829 | 2023-12-31 | 0.91363 | 0.95829
2024-01-31 | 51 | 1967986000 | 1887773400 | 2069794000 | 92895900 | 29364700 | 5904400 | 0.91206 | 0.95924 | 2024-01-31 | 0.91206 | 0.95924
2024-02-29 | 48 | 1848118600 | 1766746400 | 1947213200 | 88993600 | 27829700 | 7337200 | 0.90732 | 0.95597 | 2024-02-29 | 0.90732 | 0.95597
2024-03-31 | 50 | 1996797200 | 1915498900 | 2127650600 | 97676700 | 31101700 | 7558300 | 0.90029 | 0.95929 | 2024-03-31 | 0.90029 | 0.95929
2024-04-30 | 50 | 2074962500 | 1994155600 | 2218839800 | 102589300 | 38600700 | 9111400 | 0.89874 | 0.96106 | 2024-04-30 | 0.89874 | 0.96106
2024-05-31 | 47 | 2011425600 | 1931863200 | 2170420500 | 101830200 | 37404900 | 11269900 | 0.89009 | 0.96044 | 2024-05-31 | 0.89009 | 0.96044
2024-06-30 | 46 | 2082149800 | 2002440700 | 2240674700 | 104520700 | 37103300 | 10992100 | 0.89368 | 0.96172 | 2024-06-30 | 0.89368 | 0.96172
2024-07-31 | 47 | 2227592400 | 2146834300 | 2395782200 | 110992500 | 38550200 | 10749800 | 0.89609 | 0.96375 | 2024-07-31 | 0.89609 | 0.96375
2024-08-31 | 45 | 2046919800 | 1966740700 | 2189156050 | 104323300 | 33369800 | 8383500 | 0.8984 | 0.96083 | 2024-08-31 | 0.8984 | 0.96083
2024-09-30 | 46 | 2129417400 | 2050089000 | 2283304300 | 112168500 | 37646500 | 9459600 | 0.89786 | 0.96275 | 2024-09-30 | 0.89786 | 0.96275
2024-10-31 | 47 | 2207573400 | 2127232900 | 2359414000 | 116480400 | 37866400 | 8981100 | 0.90159 | 0.96361 | 2024-10-31 | 0.90159 | 0.96361
2024-11-30 | 46 | 2318142100 | 2236423900 | 2503308300 | 124218000 | 43092100 | 9909200 | 0.89339 | 0.96475 | 2024-11-30 | 0.89339 | 0.96475
2024-12-31 | 43 | 2224958400 | 2142835400 | 2380188200 | 120484800 | 45839900 | 9469900 | 0.90028 | 0.96309 | 2024-12-31 | 0.90028 | 0.96309
2025-01-31 | 43 | 2393277000 | 2312039500 | 2578264000 | 127154900 | 49011900 | 9469900 | 0.89674 | 0.96606 | 2025-01-31 | 0.89674 | 0.96606
2025-02-28 | 42 | 2459201700 | 2377584700 | 2639042300 | 130480700 | 51070900 | 9802200 | 0.90093 | 0.96681 | 2025-02-28 | 0.90093 | 0.96681
2025-03-31 | 42 | 2616903100 | 2532632000 | 2826432100 | 139454400 | 54746400 | 10828500 | 0.89605 | 0.9678 | 2025-03-31 | 0.89605 | 0.9678
2025-04-30 | 41 | 2643380900 | 2553920100 | 2854496600 | 141682900 | 56002400 | 12823200 | 0.8947 | 0.96616 | 2025-04-30 | 0.8947 | 0.96616
2025-05-31 | 37 | 2502671700 | 2403722300 | 2704427800 | 138387900 | 59349400 | 12364400 | 0.88881 | 0.96046 | 2025-05-31 | 0.88881 | 0.96046
2025-06-30 | 35 | 2595297200 | 2491899900 | 2803873000 | 141101100 | 61280800 | 12890600 | 0.88873 | 0.96016 | 2025-06-30 | 0.88873 | 0.96016
2025-07-31 | 33 | 2522503100 | 2417740600 | 2736985000 | 141234200 | 66260800 | 13286300 | 0.88336 | 0.95847 | 2025-07-31 | 0.88336 | 0.95847
2025-08-31 | 31 | 2264039800 | 2161799800 | 2441593800 | 121415600 | 60920100 | 15172000 | 0.88541 | 0.95484 | 2025-08-31 | 0.88541 | 0.95484
2025-09-30 | 29 | 1974164900 | 1878423300 | 2139704350 | 104140000 | 53007100 | 15252400 | 0.87789 | 0.9515 | 2025-09-30 | 0.87789 | 0.9515
2025-10-31 | 26 | 1937441000 | 1849505100 | 2124101300 | 103203900 | 54932600 | 14713500 | 0.87072 | 0.95461 | 2025-10-31 | 0.87072 | 0.95461
2025-11-30 | 25 | 1976530000 | 1896811900 | 2179745400 | 104104000 | 57847800 | 14373700 | 0.8702 | 0.95967 | 2025-11-30 | 0.8702 | 0.95967
2025-12-31 | 25 | 2052866200 | 1981777000 | 2281320500 | 108753300 | 60600000 | 14542600 | 0.8687 | 0.96537 | 2025-12-31 | 0.8687 | 0.96537

## Change_Categories
Change Order Analysis by Cause
Change_Category | Change_Count | Approved_Count | Approved_Value | Pending_Value | Approved_Schedule_Impact_Days | Avg_Approval_Days
Owner-Directed Change | 106 | 74 | 42848100 | 10166400 | 487 | 44.9324
Design Error or Omission | 106 | 72 | 31940300 | 6151600 | 635 | 42.6806
Unforeseen Condition | 69 | 52 | 23709000 | 4468600 | 700 | 47.5769
Scope Clarification | 52 | 35 | 14993500 | 940100 | 141 | 41.2
Utility Conflict | 34 | 26 | 10285900 | 615200 | 306 | 40.0769
Code or Regulatory Requirement | 28 | 17 | 9081800 | 1386400 | 136 | 44.3529
Coordination Issue | 63 | 37 | 8565800 | 2749200 | 224 | 46.1081
Material Substitution | 41 | 23 | 4388100 | 3186400 | 132 | 44.6522
Contractor-Requested Change | 36 | 20 | 4372400 | 962300 | 50 | 39.3
Weather Impact | 18 | 11 | 1433800 | 265000 | 87 | 48.8182

## RFI_Disciplines
RFI Performance by Discipline
Discipline | RFI_Count | Open_RFI_Count | Avg_Response_Days | Late_RFI_Count | Late_RFI_Rate | Total_Cost_Impact | Total_Schedule_Impact_Days
Electrical | 236 | 30 | 15.4958 | 182 | 77.12% | 2033600 | 261
Structural | 220 | 23 | 15.3318 | 171 | 77.73% | 1759900 | 229
General | 108 | 14 | 14.9074 | 83 | 76.85% | 1179900 | 120
Architectural | 277 | 44 | 14.4296 | 211 | 76.17% | 1662900 | 337
Fire Protection | 97 | 12 | 14.1546 | 72 | 74.23% | 1054000 | 124
Plumbing | 158 | 27 | 14.1392 | 112 | 70.89% | 1981900 | 150
Mechanical | 240 | 37 | 14.0083 | 177 | 73.75% | 1921600 | 254
Civil | 178 | 33 | 13.8764 | 130 | 73.03% | 1400200 | 181

## Definitions_Thresholds
Metric Definitions and Project Health Thresholds
Metric | Formula | Interpretation | Use | Implementation | Basis
CPI | Earned Value / Actual Cost | >1 favorable; <1 unfavorable | Cost efficiency | Formula-driven | EVM
SPI | Earned Value / Planned Value | >1 ahead; <1 behind | Schedule efficiency | Formula-driven | EVM
CV | Earned Value − Actual Cost | Negative is unfavorable | Cost variance | Formula-driven | EVM
SV | Earned Value − Planned Value | Negative is unfavorable | Schedule variance | Formula-driven | EVM
EAC | BAC / CPI | Forecast final cost | Cost forecast | Formula-driven | EVM
VAC | BAC − EAC | Negative indicates overrun | Forecast variance | Formula-driven | EVM
Schedule Delay | Forecast End − Planned End | Positive indicates delay | Calendar forecast | Formula-driven | Project dates
Contingency Burn Ratio | Contingency Utilization / Progress | >1 means contingency is being used faster than progress | Early warning | Formula-driven | Portfolio assumption
Health | CPI | SPI | Forecast Overrun | Schedule Delay | Contingency Utilization | Contingency Burn Ratio
Green | ≥ 0.95 | ≥ 0.95 | ≤ 5% | ≤ 15 days | ≤ 75% | ≤ 1.20x
Yellow | 0.90–0.95 | 0.90–0.95 | > 5% to 10% | > 15 to 30 days | > 75% to 90% | > 1.20x to 1.50x
Red | < 0.90 | < 0.90 | > 10% | > 30 days | > 90% | > 1.50x
Classification rule: a project is Red when any Red threshold is breached. If no Red threshold is breached, it is Yellow when any Yellow threshold is breached; otherwise it is Green. These are portfolio assumptions approved in the ASK phase—not universal construction standards.

## Dashboard_Data
Metric | Value | Health Status | Projects | Project Type | Projects | Forecast Overrun % | Avg Delay Days | Rank | Project ID | Project Name | Forecast Overrun % | Delay Days | CPI | Reporting Date | Weighted CPI | Weighted SPI | Change Category | Approved Value | Schedule Impact Days | Discipline | Avg Response Days | Late RFI Rate | Relationship | Pearson r | Strength | Interpretation | Project Type | Forecast Overrun % | Month | Weighted CPI | Weighted SPI
Project Count | 75 | Red | 50 | Mixed-Use | 11 | 0.16344 | 46.8182 | 1 | PRJ-075 | Canyon Ridge Transit-Oriented Development | 0.32871 | 73 | 0.75261 | 2022-01-31 | 0.93833 | 0.94777 | Owner-Directed Change | 42848100 | 487 | Electrical | 15.4958 | 0.77119 | Approved CO % vs Cost Growth % | 0.99977 | Strong | strong positive association; does not establish causation. | Mixed-Use | 16.34% | Jan-22 | 0.93833 | 0.94777
Total BAC | 5831436600 | Yellow | 13 | Residential | 14 | 0.13963 | 35 | 2 | PRJ-009 | Northstar Housing | 0.32487 | 63 | 0.75479 | 2022-02-28 | 0.92401 | 0.94656 | Design Error or Omission | 31940300 | 635 | Structural | 15.3318 | 0.77727 | Approved CO % vs Forecast Overrun % | 0.40047 | Moderate | moderate positive association; does not establish causation. | Residential | 13.96% | Feb-22 | 0.92401 | 0.94656
Total EAC | 6586989965.6969 | Green | 12 | Industrial | 9 | 0.13911 | 25.5556 | 3 | PRJ-046 | Red Rock Residences | 0.28368 | 84 | 0.77901 | 2022-03-31 | 0.93301 | 0.94598 | Unforeseen Condition | 23709000 | 700 | General | 14.9074 | 0.76852 | Average RFI Response Days vs Schedule Delay Days | 0.51695 | Moderate | moderate positive association; does not establish causation. | Industrial | 13.91% | Mar-22 | 0.93301 | 0.94598
Forecast Overrun % | 0.12957 |  |  | Commercial | 13 | 0.12231 | 30.6923 | 4 | PRJ-068 | Canyon Ridge Bridge Rehabilitation | 0.25904 | 55 | 0.79426 | 2022-04-30 | 0.92534 | 0.94683 | Scope Clarification | 14993500 | 141 | Architectural | 14.4296 | 0.76173 | Late RFI Rate vs Schedule Delay Days | 0.34281 | Modest | modest positive association; does not establish causation. | Commercial | 12.23% | Apr-22 | 0.92534 | 0.94683
Weighted CPI | 0.88417 |  |  | Institutional | 18 | 0.11272 | 44.9444 | 5 | PRJ-034 | Mountain Gate Community College | 0.24175 | 38 | 0.80532 | 2022-05-31 | 0.92667 | 0.94799 | Utility Conflict | 10285900 | 306 | Fire Protection | 14.1546 | 0.74227 | Contingency Burn Ratio vs Forecast Overrun % | 0.90084 | Strong | strong positive association; does not establish causation. | Institutional | 11.27% | May-22 | 0.92667 | 0.94799
Weighted SPI | 0.98717 |  |  | Heavy Civil & Infrastructure | 10 | 0.094074 | 8.3 | 6 | PRJ-017 | Westfield Retail Center | 0.22911 | 48 | 0.8136 | 2022-06-30 | 0.91927 | 0.9491 | Code or Regulatory Requirement | 9081800 | 136 | Plumbing | 14.1392 | 0.70886 | RFI Density vs Schedule Delay Days | -0.057826 | Weak | weak negative association; does not establish causation. | Heavy Civil & Infrastructure | 9.407% | Jun-22 | 0.91927 | 0.9491
Average Delay Days | 33.68 | [6 empty] | 7 | PRJ-064 | Evergreen Townhomes | 0.2258 | 34 | 0.81579 | 2022-07-31 | 0.91138 | 0.95027 | Coordination Issue | 8565800 | 224 | Mechanical | 14.0083 | 0.7375 | CO Density vs Forecast Overrun % | 0.15211 | Weak | weak positive association; does not establish causation. |  |  | Jul-22 | 0.91138 | 0.95027
Contingency Utilization % | 0.66226 | [6 empty] | 8 | PRJ-013 | Sunrise Housing | 0.22061 | 61 | 0.81926 | 2022-08-31 | 0.90596 | 0.95391 | Material Substitution | 4388100 | 132 | Civil | 13.8764 | 0.73034 | [6 empty] | Aug-22 | 0.90596 | 0.95391
Red Projects | 50 | [6 empty] | 9 | PRJ-069 | Cedar Valley Town Center | 0.17763 | 104 | 0.84916 | 2022-09-30 | 0.90662 | 0.95701 | Contractor-Requested Change | 4372400 | 50 | [9 empty] | Sep-22 | 0.90662 | 0.95701
Yellow Projects | 13 | [6 empty] | 10 | PRJ-025 | Blue Mesa Public Safety Center | 0.12018 | 87 | 0.89271 | 2022-10-31 | 0.91526 | 0.95953 | Weather Impact | 1433800 | 87 | [9 empty] | Oct-22 | 0.91526 | 0.95953
Green Projects | 12 | [12 empty] | 2022-11-30 | 0.91547 | 0.96013 | [12 empty] | Nov-22 | 0.91547 | 0.96013
Approved CO Value | 151618700 | [12 empty] | 2022-12-31 | 0.91566 | 0.9587 | [12 empty] | Dec-22 | 0.91566 | 0.9587
Pending CO Value | 30891200 | [12 empty] | 2023-01-31 | 0.91392 | 0.95958 | [12 empty] | Jan-23 | 0.91392 | 0.95958
[14 empty] | 2023-02-28 | 0.91713 | 0.96073 | [12 empty] | Feb-23 | 0.91713 | 0.96073
[14 empty] | 2023-03-31 | 0.91007 | 0.96045 | [12 empty] | Mar-23 | 0.91007 | 0.96045
[14 empty] | 2023-04-30 | 0.91569 | 0.95706 | [12 empty] | Apr-23 | 0.91569 | 0.95706
[14 empty] | 2023-05-31 | 0.91905 | 0.95687 | [12 empty] | May-23 | 0.91905 | 0.95687
[14 empty] | 2023-06-30 | 0.91647 | 0.95734 | [12 empty] | Jun-23 | 0.91647 | 0.95734
[14 empty] | 2023-07-31 | 0.91209 | 0.95325 | [12 empty] | Jul-23 | 0.91209 | 0.95325
[14 empty] | 2023-08-31 | 0.91285 | 0.95475 | [12 empty] | Aug-23 | 0.91285 | 0.95475
[14 empty] | 2023-09-30 | 0.91913 | 0.95442 | [12 empty] | Sep-23 | 0.91913 | 0.95442
[14 empty] | 2023-10-31 | 0.91837 | 0.95644 | [12 empty] | Oct-23 | 0.91837 | 0.95644
[14 empty] | 2023-11-30 | 0.92105 | 0.95693 | [12 empty] | Nov-23 | 0.92105 | 0.95693
[14 empty] | 2023-12-31 | 0.91363 | 0.95829 | [12 empty] | Dec-23 | 0.91363 | 0.95829
[14 empty] | 2024-01-31 | 0.91206 | 0.95924 | [12 empty] | Jan-24 | 0.91206 | 0.95924
[14 empty] | 2024-02-29 | 0.90732 | 0.95597 | [12 empty] | Feb-24 | 0.90732 | 0.95597
[14 empty] | 2024-03-31 | 0.90029 | 0.95929 | [12 empty] | Mar-24 | 0.90029 | 0.95929
[14 empty] | 2024-04-30 | 0.89874 | 0.96106 | [12 empty] | Apr-24 | 0.89874 | 0.96106
[14 empty] | 2024-05-31 | 0.89009 | 0.96044 | [12 empty] | May-24 | 0.89009 | 0.96044
[14 empty] | 2024-06-30 | 0.89368 | 0.96172 | [12 empty] | Jun-24 | 0.89368 | 0.96172
[14 empty] | 2024-07-31 | 0.89609 | 0.96375 | [12 empty] | Jul-24 | 0.89609 | 0.96375
[14 empty] | 2024-08-31 | 0.8984 | 0.96083 | [12 empty] | Aug-24 | 0.8984 | 0.96083
[14 empty] | 2024-09-30 | 0.89786 | 0.96275 | [12 empty] | Sep-24 | 0.89786 | 0.96275
[14 empty] | 2024-10-31 | 0.90159 | 0.96361 | [12 empty] | Oct-24 | 0.90159 | 0.96361
[14 empty] | 2024-11-30 | 0.89339 | 0.96475 | [12 empty] | Nov-24 | 0.89339 | 0.96475
[14 empty] | 2024-12-31 | 0.90028 | 0.96309 | [12 empty] | Dec-24 | 0.90028 | 0.96309
[14 empty] | 2025-01-31 | 0.89674 | 0.96606 | [12 empty] | Jan-25 | 0.89674 | 0.96606
[14 empty] | 2025-02-28 | 0.90093 | 0.96681 | [12 empty] | Feb-25 | 0.90093 | 0.96681
[14 empty] | 2025-03-31 | 0.89605 | 0.9678 | [12 empty] | Mar-25 | 0.89605 | 0.9678
[14 empty] | 2025-04-30 | 0.8947 | 0.96616 | [12 empty] | Apr-25 | 0.8947 | 0.96616
[14 empty] | 2025-05-31 | 0.88881 | 0.96046 | [12 empty] | May-25 | 0.88881 | 0.96046
[14 empty] | 2025-06-30 | 0.88873 | 0.96016 | [12 empty] | Jun-25 | 0.88873 | 0.96016
[14 empty] | 2025-07-31 | 0.88336 | 0.95847 | [12 empty] | Jul-25 | 0.88336 | 0.95847
[14 empty] | 2025-08-31 | 0.88541 | 0.95484 | [12 empty] | Aug-25 | 0.88541 | 0.95484
[14 empty] | 2025-09-30 | 0.87789 | 0.9515 | [12 empty] | Sep-25 | 0.87789 | 0.9515
[14 empty] | 2025-10-31 | 0.87072 | 0.95461 | [12 empty] | Oct-25 | 0.87072 | 0.95461
[14 empty] | 2025-11-30 | 0.8702 | 0.95967 | [12 empty] | Nov-25 | 0.8702 | 0.95967
[14 empty] | 2025-12-31 | 0.8687 | 0.96537 | [12 empty] | Dec-25 | 0.8687 | 0.96537

## Executive_Dashboard
Construction Project Controls Executive Dashboard
Early-warning view of cost, schedule, contingency, change-order, and RFI exposure across 75 synthetic U.S. construction projects. Portfolio reporting period: 2022–2025.
PORTFOLIO BAC |  |  |  | FORECAST EAC |  |  |  | FORECAST OVERRUN | PROJECTS AT RED STATUS
5831436600 |  |  |  | 6586989965.6969 |  |  |  | 12.96% | 50
WEIGHTED CPI |  |  |  | WEIGHTED SPI |  |  |  | AVERAGE FORECAST DELAY | CONTINGENCY UTILIZATION
0.88417 |  |  |  | 0.98717 |  |  |  | 33.68 | 66.23%
Portfolio Risk Distribution | [7 empty] | Forecast Overrun by Project Type
Top 10 Projects Requiring Management Attention | [7 empty] | Monthly CPI and SPI Trend
Rank | Project ID | Project Name | Forecast Overrun | Delay | CPI | Status | Primary Driver
1 | PRJ-075 | Canyon Ridge Transit-Oriented Development | 32.87% | 73 | 0.75261 | Red | CPI < 0.90
2 | PRJ-009 | Northstar Housing | 32.49% | 63 | 0.75479 | Red | CPI < 0.90
3 | PRJ-046 | Red Rock Residences | 28.37% | 84 | 0.77901 | Red | CPI < 0.90
4 | PRJ-068 | Canyon Ridge Bridge Rehabilitation | 25.9% | 55 | 0.79426 | Red | CPI < 0.90
5 | PRJ-034 | Mountain Gate Community College | 24.17% | 38 | 0.80532 | Red | CPI < 0.90
6 | PRJ-017 | Westfield Retail Center | 22.91% | 48 | 0.8136 | Red | CPI < 0.90
7 | PRJ-064 | Evergreen Townhomes | 22.58% | 34 | 0.81579 | Red | CPI < 0.90
8 | PRJ-013 | Sunrise Housing | 22.06% | 61 | 0.81926 | Red | CPI < 0.90
9 | PRJ-069 | Cedar Valley Town Center | 17.76% | 104 | 0.84916 | Red | CPI < 0.90
10 | PRJ-025 | Blue Mesa Public Safety Center | 12.02% | 87 | 0.89271 | Red | CPI < 0.90
Executive Interpretation
1. Cost performance is the main portfolio exposure: weighted CPI is 0.884, with a forecast overrun of 13.0%.
2. Calendar delay remains material even though weighted SPI is near 1.00; average forecast delay is 33.7 days.
3. Mixed-Use has the highest forecast overrun (16.3%); Heavy Civil & Infrastructure is lowest (9.4%).
4. Contingency burn ratio is the strongest tested early-warning relationship with forecast overrun (r = 0.901).
5. Average RFI response time has a moderate positive association with schedule delay (r = 0.517).
6. Formal management recommendations and implementation priorities will be completed in the ACT phase.
Disclosure: synthetic portfolio data; associations do not establish causation and are not construction-industry benchmarks.

## Operational_Insights
Operational Insights: Change Orders, RFIs, and Warning Indicators
Diagnostic views showing which change categories, RFI disciplines, and project-control indicators deserve management attention. Results are based on the synthetic portfolio and should be interpreted as associations.
Approved Change Value by Cause | [7 empty] | Average RFI Response Time by Discipline
Relationship Testing | [7 empty] | Key Diagnostic Messages
Relationship | Pearson r | Strength | Direction | R² | Use | Caution | Priority | Owner-directed changes represent the largest approved value: $42.8M.
Approved CO % vs Cost Growth % | 0.99977 | Strong | Positive | 0.99955 | Contextual comparison | Association only; no causal proof. | Low
Approved CO % vs Forecast Overrun % | 0.40047 | Moderate | Positive | 0.16037 | Change exposure review | Association only; no causal proof. | Medium
Average RFI Response Days vs Schedule Delay Days | 0.51695 | Moderate | Positive | 0.26723 | Response-time governance | Association only; no causal proof. | High | Design errors or omissions account for $31.9M in approved value.
Late RFI Rate vs Schedule Delay Days | 0.34281 | Modest | Positive | 0.11752 | Late-response monitoring | Association only; no causal proof. | Medium
Contingency Burn Ratio vs Forecast Overrun % | 0.90084 | Strong | Positive | 0.8115 | Early-warning monitoring | Association only; no causal proof. | High
RFI Density vs Schedule Delay Days | -0.057826 | Weak | Negative | 0.0033438 | Contextual comparison | Association only; no causal proof. | Low | Unforeseen conditions produce the largest approved schedule impact: 700 days.
CO Density vs Forecast Overrun % | 0.15211 | Weak | Positive | 0.023138 | Contextual comparison | Association only; no causal proof. | Low
Electrical RFIs have the longest average response time: 15.5 days.
Structural RFIs average 15.3 response days.
RFI response timeliness is more analytically useful than raw RFI density in this portfolio.
Share-Phase Communication Notes
Audience: executive leadership, project-controls management, project managers, cost managers, and schedulers.
Message hierarchy: portfolio exposure → projects requiring attention → contributing patterns → evidence limitations.
Accessibility: high-contrast headings, status labels paired with text, limited color dependence, readable number formats, and concise annotations.
Interactivity path: use the project-level CSV or SQLite view as the data source for Tableau or Power BI filters and drill-down.
Portfolio use: publish dashboard images with a short narrative; link to GitHub or the downloadable case-study report for methodology and SQL.
Company use: position the dashboard as an In Project LLC demonstration of construction project-controls analytics—not as actual client performance.